## Sheet1
MFT Migration analysis Summary :
# of hosts | 4
# of mailboxes | 4
# of actions | 6
# of actions to be migrated with Informatica migration tool | 1
# of actions to be migrated with A.B LINK migration tool | 4
# of actions requires manual handling | 1
Detailed Analysis :
HOST | MAILBOX | ACTION | COMMANDS | TRANSPORT | ANALYSYS ("as is" state) | MIGRATION_PLAN
Sweden_SFTP | Sweden | receive | # Receive all files from remote host cd /Sverige GET -DEL file.txt | SSH FTP | - MULTIPLE COMMANDS ACTION - NON-DX ENDPOINT | ABlink migration utility
Acme_FTP | US_mailbox | receive | Get * | FTP | - STANDARD ACTION | Informatica Migration tool
Local FTP Users | myTradingPartner | release | # Release all not yet available files LCOPY -DEL -UNI %outbox%/../* %outbox% | FTP | - CLEO COMMANDS, - NON-DX ENDPOINT | ABlink migration utility
Local FTP Users | myTradingPartner | collect | # Initialize inbound file LDELETE recvfile.edi # Merge all files received into recvfile.edi LCOPY -DEL -APE %inbox%/* recvfile.edi | FTP | - CLEO COMMANDS - MULTIPLE COMMANDS - NON-DX ENDPOINT | ABlink migration utility
Local FTP Users | myTradingPartner | release | ## This action is setup as part of DS to EAI migration Wave 1 - CHG0031956 ## # Create envelope with processing error status to notify that file not available at remote location SET ExecuteOnCheckConditionsNotMet=/eai/apps/framework/bin/run_file_bootstrap -e PRD -c BOOTSTRAP_DELIVERY_NOTIFICATIONS_FROM_VMN_SAP -f %destfile% -t &quot;%transferid%&quot; -s %status% # Bootstrap component for on-boarding AP Recovery Delivery Notifications from VMN-SAP SET ExecuteOnSuccessfulReceive=/usr/local | FTP | - CLEO COMMANDS, - NON-DX ENDPOINT | Manual migration
Generic HTTP | myMailbox | send | # Send files to remote host PUT * | HTTP | - NON-DX ENDPOINT | ABlink migration utility